## Slide 1: SKILL SEEKER
Project plan for the Initiation phase

## Slide 2: 01 02 03 TABLE OF CONTENTS 04 05 06
Background
Deliverables
Business case
Planning
Scope and risk management
Information and reporting
07
The team

## Slide 3: Background 01

## Slide 4: Background
The company:
Mediaan.com
Sales department
IT and consultancy company
Reason for project
Streamline the process of assigning developers to projects. Current way is too slow.

## Slide 5: Deliverables 02

## Slide 6: Deliverables
Easy to use application
Application which will recommend employees based on the skills required by the given project
Documentation and user manual

## Slide 7: Business case 03

## Slide 8: Efficient Resource Allocation

## Slide 9: Increased Employee Productivity

## Slide 10: Skill Development and Utilization

## Slide 11: Planning 04

## Slide 12: Planning
Phase 1: Researching possibilities and technologies
Deadline: March 8th, 2024
Phase 2: Realization
Deadline: May 24th, 2024
Phase 3: Information & Reporting
Deadline: May 31st, 2024

## Slide 13: Phase 1
Market research for existing solutions
Research for technology to be used
  Tech stack
  DBMS
Create wireframes
Define functional must have requirements
Design data model
Deadline: March 8th, 2024

## Slide 14: Phase 2
Creation of database
Creation of front-end
  3 sections
    Login page
    Employee
      Employee list page
      Employee details page
    Project
      Project list page
      Project details page
Creation of back-end
Hosting application
Deadline: May 24th, 2024

## Slide 15: Phase 3: Information and Reporting
Finalize documentation
Prepare final presentation for client
Deadline May 31st, 2024

## Slide 16: Scope and risk management 05

## Slide 17: Out of scope
Filtering employees based on skill set.
Filtering employees based on name.
Skill matrix for better matching.
Employees can edit their own information.
Admin can edit anyone's information.
Integrating Azure AD.
Tailor made CV generation.
Personal development trajectory.
Matching with the usage of AI.
Adding new skills.
Editing relationship score between skills.
In scope

## Slide 18: Risk analysis and measures
Miscommunication:
  Little communication with client
  Solution: Intermediate alignment meetings
User adoption:
  Sales department employees not adopting the new system
  Solution: Give proper training after the application is finished

## Slide 19: Information and Reporting 06

## Slide 20: Information and Reporting
Intermediate alignment meeting
  Review of current state at the time.
  Share insights .
Final reporting
  Location: Mediaan Hasselt.
  Presentation of final product.
  Deliver reports/documentation.
  Final reporting: May 31st, 2024

## Slide 21: The Team 07

## Slide 22
Samuel | Robin | Salih | Cisse

## Slide 23: THANKS!
Do you have any questions?